## Gantchart
GANTT CHART
PROJECT TITLE |  | HOME AUTOMATION USING AI |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P Shah Institute of Technology
PROJECT GUIDE |  | Prof. KIRAN DESHPANDE, Prof. UTTAM KOLEKAR |  |  |  |  | DATE | [6 empty] | 2021-02-27
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Akhil, Sagar, Saunvid | 2020-01-20 | 2020-02-08 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Research paper finalization | Akhil, Sagar, Saunvid | 2020-02-08 | 2020-02-26 | 3 | 100% | bar: WEEK 2 W
1.2 | Project Title | Akhil, Sagar, Saunvid | 2020-02-28 | 2020-03-14 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Akhil | 2020-03-14 | 2020-03-20 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Objectives | Akhil, Sagar, Saunvid | 2020-03-21 | 2020-03-27 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Literature Review | Akhil, Sagar | 2020-03-28 | 2020-04-03 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Akhil | 2020-03-05 | 2020-03-12 | 1 | 100% | bar: WEEK 3 F
1.7 | Scope | Akhil | 2020-03-05 | 2020-03-05 | 1 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Sagar, Saunvid | 2020-03-05 | 2020-03-05 | 1 | 100% | bar: WEEK 3 F
1.9 | Applications | Saunvid | 2020-03-05 | 2020-03-05 | 1 | 100% | bar: WEEK 3 F
2 | Project Design
2.1 | Proposed System | Akhil, Sagar, Saunvid | 2020-09-19 | 2020-10-06 | 2 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Akhil, Sagar, Saunvid | 2020-09-19 | 2020-10-06 | 2 | 100% | bar: WEEK 4 F to WEEK 5 F
2.3 | Activity Diagram | Akhil, Sagar, Saunvid | 2020-09-19 | 2020-10-06 | 2 | 100%
2.4 | Use Case Diagram | Akhil, Sagar, Saunvid | 2020-09-19 | 2020-10-06 | 2 | 100%
2.5 | Description Of Use Case | Akhil, Sagar | 2020-09-19 | 2020-10-06 | 2 | 100%
2.6 | Modules
2.6.1 | Android app home page module | Akhil, Sagar, Saunvid | 2020-09-19 | 2020-10-06 | 2 | 100%
2.6.2 | Android app Bluetooth module | Akhil, Sagar, Saunvid | 2020-09-19 | 2020-10-06 | 2 | 100%
2.6.3 | Arduino EDE Module | Akhil, Sagar, Saunvid | 2020-09-19 | 2020-10-06 | 2 | 100%
2.6.4 | Rasphberry pie module | Akhil, Sagar, Saunvid | 2020-09-19 | 2020-10-06 | 2 | 100%
2.7 | Preparation Of Report | Akhil | 2020-09-19 | 2020-10-06 | 2 | 100%
3 | Project Implementation
3.1 | Arduino implementation | Akhil, Sagar, Saunvid | 2021-01-25 | 2021-03-15 | 4 | 100%
3.2 | Rasphberry pie implementation | Akhil, Sagar, Saunvid | 2021-01-25 | 2021-03-15 | 8 | 100%
3.3 | Door lock implementation | Akhil, Sagar, Saunvid | 2021-01-25 | 2021-03-15 | 6 | 100%
4 | Testing
4.1 | Design of Test Cases | Sagar, Saunvid | 2021-03-03 | 2021-03-09 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 T to WEEK 2 F; WEEK 3 T to WEEK 3 F
4.2 | Architecture | Akhil, Saunvid | 2021-03-10 | 2021-03-16 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.3 | Prototyping | Akhil, Sagar, Saunvid | 2021-03-17 | 2021-03-23 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.4 | Development | Sagar, Saunvid | 2021-03-24 | 2021-03-30 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.5 | Testing QA | Akhil, Saunvid | 2021-03-31 | 2021-04-06 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
5 | Results and Analyis
5.1 | Report Preparation | Akhil | 2021-02-25 | 2021-02-26 | 1 | 100%